## Sheet1
Activity/Module | Details | Start Date | End Date | Infy SME | Delottie SME | Status | Comments
VZTIME
| Environment details | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed |  | https://docs.google.com/spreadsheets/d/1vAntX0sHTBx3x_PkURV7duzhGkjFLERt/edit#gid=1291495359
| Host Details | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed |  | https://docs.google.com/spreadsheets/d/1vAntX0sHTBx3x_PkURV7duzhGkjFLERt/edit#gid=1291495359
| scripts (start/stop) | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed |  | https://docs.google.com/document/d/1WRS7-XsGMyAfKvFQMbgiqlavDyC7PHvn/edit
| LB setup | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Pending | Google drive link need to update | https://docs.google.com/document/d/1WRS7-XsGMyAfKvFQMbgiqlavDyC7PHvn/edit
| casino configuration | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Pending | Need to check the LB setup | https://docs.google.com/document/d/1XckMtQ7nYo1SC1l2lOyoTM-vej-GJ4aO/edit
| cert renewal |  |  | Ali | Siva/Naresh | Pending | yet to confirm with mehboob.ali1@verizon.com
| Logs path | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed |  | https://docs.google.com/document/d/1T5L9D97FU5u0jNtRtk5ffqbxTYlULgRL/edit
| Maintenance activities | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed |  | https://docs.google.com/document/d/1gLw_spL8V8PdaReNlQG6lT-UD7M10Bdj/edit
| Jenkins build and deployment | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed |  | https://docs.google.com/document/d/1WRS7-XsGMyAfKvFQMbgiqlavDyC7PHvn/edit
| ELK/Logstash | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed |  | https://docs.google.com/document/d/1WRS7-XsGMyAfKvFQMbgiqlavDyC7PHvn/edit
| Cognos setup | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed | need to follow the document | https://docs.google.com/document/d/1DgUUxNFsXiwrKBfiM6vdvrjaRILAyAW9/edit#heading=h.gjdgxs
| Cognos startup /shutdown scripts | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed | need to follow the document | https://docs.google.com/document/d/1T5L9D97FU5u0jNtRtk5ffqbxTYlULgRL/edit
| Micro Services setup | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed | need to follow the document | https://docs.google.com/document/d/1T5L9D97FU5u0jNtRtk5ffqbxTYlULgRL/edit
| Logs path | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed |  | https://docs.google.com/document/d/1T5L9D97FU5u0jNtRtk5ffqbxTYlULgRL/edit
| Infor Support Details | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed |  | https://drive.google.com/drive/folders/1Zllx0HptNp40snPVW3PMp1uofwUsrPmi
| Weekly Release | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed | need to follow the document | https://drive.google.com/drive/folders/1D9gLZl9tnd5ozQ0ue_YEjOMff4ukUQGK
| mftp setup | 2024-07-05 | 2024-07-05 | Ashok/Parag | Siva/Naresh | Completed | need to follow the document | https://docs.google.com/document/d/17ztUwEy4YWbRoR_i8ynaXmAxdYTX3J8E/edit
| DMU migrations |  |  | Ali | Siva/Naresh | Pending | Neet to check
| DR Drill |  |  | Ashok/Parag | Siva/Naresh | Pending | Ashok need to provide the more details
| Netgroups to place access requests for the environment |  |  | Ashok/Parag | Siva/Naresh | Completed | Similar to BAU access
| URLs and passwords if any |  |  | Ashok/Parag | Siva/Naresh | Completed | Placed in inventory
| Back up strategy(frequency , where they are stored..etc) |  |  | Ashok/Parag | Siva/Naresh | N/A | as per ashok it is not applicable
| any cron jobs or scripts to maintain |  |  | Ashok/Parag | Siva/Naresh | N/A | as per ashok it is not applicable
| isssues so far faced post migration , root caused and their fixes |  |  | Ashok/Parag | Siva/Naresh | Pending | Submitted SR with infor support
| application custodian, important contacts |  |  | Ashok/Parag | Siva/Naresh | Completed | koushik kundu and Team