## Task Plan _DR Dry Run_East
Pre-tasks | Owner | Date | EST Timing | IST Timing | Contact Details | Status
Create a Change request for DR dryrun | Azeem Hirani/ Mahesh | 2026-02-05 | 21:00 |  |  | Completed
Run through the task list share it over an email | Bivek | 2026-02-05 | 21:00 |  |  | Completed
Get the signoff for the plan | Nikhil | 2026-02-05 | 21:00 |  |  | Completed
Send out an email to application team for the agreed dates for DR dry run | Gnanavel | 2026-02-05 | 21:00 |  |  | Completed
End user communication or any other users to be informed | Nikhil | 2026-02-05 | 21:00 |  |  | Completed
Check the App and Web Certificate Expiration | Bivek/Gnanavel | 2026-02-05 | 21:00
DR dryrun tasks
Wait for App team confirmation to validate the application traffic both east and west regions | Hemanth/mani Divya/Nikhil/Tanya | 2026-02-13 | 21:00 | 7:30 AM 14 Feb | Tanya Srivastava Ph No: 8800998725 | Completed
Bring down the services of east YZ webservers | Gnanavel | 2026-02-13 | 21:05 |  | Gnanavel | Completed
Disable the Cronjobs in both app & Webservers in Eastzone if anything required | Gnanavel | 2026-02-13 | 21:10 |  | Gnanavel | Completed
Switch over the Databse from East to West | Rani Bolla/Swarnavikram Mani | 2026-02-13 | 21:15 |  |  | Completed
In Casino loadbalancer, disable East zone Servers pool application and internal | Gnanavel | 2026-02-13 | 21:20 |  |  | Completed
Enable all required Cronjobs | Gnanavel | 2026-02-13 | 21:20 |  |  | Completed
Request App team to perform app functionality validations | Gnanavel | 2026-02-13 | 21:20
Testing and Validation on West regeion
1.Validate Internal and External Application | Hemanth/mani Divya/Nikhil/Tanya | 2026-02-13 | 21:20 | 7:50 AM 14 Feb | Tanya Srivastava Ph No: 8800998725
2.check the applicaiton traffic flowing through proper WEST IP servers (via splunk "server_host" element) | Hemanth/mani Divya/Nikhil/Tanya | 2026-02-13 | 21:20 |  | Tanya Srivastava Ph No: 8800998725
3.Checking cron job configuration | Hemanth/mani Divya/Nikhil/Tanya | 2026-02-13 | 21:20 |  | Tanya Srivastava Ph No: 8800998725
5.Validate NewRelic Logs | Hemanth/mani Divya/Nikhil/Tanya | 2026-02-13 | 21:20 |  | Tanya Srivastava Ph No: 8800998725
DR dryrun success/failure | Hemanth/mani Divya/Nikhil/Tanya | 2026-02-13 | 21:20 |  | Tanya Srivastava Ph No: 8800998725
Rollback task
Disable all Cronjobs from west zone servers | Gnanavel | 2026-02-13 | 22:00 |  | Gnanavel | Completed
Start httpd services in east zone | Gnanavel | 2026-02-13 | 22:00 |  | Gnanavel | Completed
In Loadbalancer, enable east zone Servers pool in bot happlication and int | Gnanavel | 2026-02-13 | 22:00 |  | Gnanavel | Completed
Switch over the Databse from West to East | Rani Bolla/Swarnavikram Mani | 2026-02-13 | 22:00 |  | Rani Bolla/Swarnavikram Mani | Completed
Verify & Enable all required cronjobs in Eastzone | Gnanavel | 2026-02-13 | 22:00 |  | Gnanavel | Completed
Request application team to perform app functinality validations | Gnanavel | 2026-02-13 | 22:00 |  | Gnanavel | Completed
Testing and Validation post DR on east zone services
1.Validate Internal and External Application with Rep and test Customer login | Hemanth/mani Divya/Nikhil | 2026-02-13 | 23:00 |  | Tanya Srivastava Ph No: 8800998725 | Completed
2.check the applicaiton traffic flowing through proper EAST /WEST IP servers (via splunk "server_host" element) | Hemanth/mani Divya/Nikhil | 2026-02-13 | 23:00 |  | Tanya Srivastava Ph No: 8800998725 | Completed
3.Check Activate lot status and last execution date in Espx table in DB (also check update_stock job weather it is in inprogress or completed) | Hemanth/mani Divya/Nikhil | 2026-02-13 | 23:00 |  | Tanya Srivastava Ph No: 8800998725 | Completed
4.Post Cron job start validate activateLot /updateLotShipmentDetails and application logs from splunk and elk | Hemanth/mani Divya/Nikhil | 2026-02-13 | 23:00 |  | Tanya Srivastava Ph No: 8800998725 | Completed
5.Validate NewRelic Logs | Hemanth/mani Divya/Nikhil | 2026-02-13 | 23:00 |  | Tanya Srivastava Ph No: 8800998725 | Completed
Post DR Drill
Sending status communication mail to Stakeholders | Azeem/Mahesh | 2026-02-13 | 23:00
Fusion Portal Update | Azeem | 2026-02-13 | 23:00
Closing of Change request and Ctasks | Azeem/Mahesh | 2026-02-13 | 23:00

## TaskPlan_DR_East
Pre-tasks |  | Date | EST Timing | IST Timing | Owner | Contact Details | Status
CDN Akamai west regeion should be configured | Ranil | 2026-02-13 | 20:00
Create a Change request for DR dryrun | Azeem Hirani | 2026-02-13 | 20:00
Run through the task list share it over an email | Bivek | 2026-02-13 | 20:00
Get the signoff for the plan | Nikhil | 2026-02-13 | 20:00
Send out an email to application team for the agreed dates for DR dry run | Gnanavel | 2026-02-13 | 20:00
End user communication or any other users to be informed | Nikhil | 2026-02-13 | 20:00
Check the App and Web Certificate Expiration | Bivek/Gnanavel | 2026-02-13 | 20:00
DR dryrun tasks
Wait for App team confirmation to check the current job is in completed state. | Hemanth/mani Divya/Nikhil | 2026-02-13 | 21:00
Bring down the services of east YZ webservers | Gnanavel/Nikhil | 2026-02-13 | 21:00
Disable the Cronjobs in both app & Webservers in Eastzone if anything required | Gnanavel | 2026-02-13 | 21:00
Switch over the Databse from East to West | Swarnavikram Mani/Madhusudhan | 2026-02-13 | 21:00
In Casino loadbalancer, disable East zone Servers pool application and internal | Gnanavel | 2026-02-13 | 21:00
Enable all required Cronjobs | Gnanavel | 2026-02-13 | 21:00
Request App team to perform app functionality validations | Gnanavel | 2026-02-13 | 21:00
Testing and Validation on West regeion
1.Validate Internal and External Application with Rep and test Customer login | Hemanth/mani Divya/Nikhil | 2026-02-13 | 21:00
2.check the applicaiton traffic flowing through proper WEST IP servers (via splunk "server_host" element) | Hemanth/mani Divya/Nikhil | 2026-02-13 | 21:00
3.Check Activate lot status and last execution date in Espx table in DB (also check update_stock job weather it is in inprogress or completed) | Hemanth/mani Divya/Nikhil | 2026-02-13 | 21:00
4.Post Cron job start validate activateLot /updateLotShipmentDetails and application logs from splunk and elk | Hemanth/mani Divya/Nikhil | 2026-02-13 | 21:00
5.Validate NewRelic Logs | Hemanth/mani Divya/Nikhil | 2026-02-13 | 21:00
DR dryrun success/failure | Hemanth/mani Divya/Nikhil
Rollback task
Disable all Cronjobs from west zone servers | Gnanavel | 2026-02-13 | 22:00
Start httpd services in east zone | Gnanavel/Nikhil | 2026-02-13 | 22:00
In Loadbalancer, enable east zone Servers pool in bot happlication and int | Gnanavel | 2026-02-13 | 22:00
Switch over the Databse from West to East | Swarnavikram Mani/Madhusudhan | 2026-02-13 | 22:00
Verify & Enable all required cronjobs in Eastzone | Gnanavel | 2026-02-13 | 22:00
Request application team to perform app functinality validations | Gnanavel | 2026-02-13 | 22:00
Testing and Validation post DR on east zone services
1.Validate Internal and External Application with Rep and test Customer login | Hemanth/mani Divya/Nikhil | 2026-02-13 | 23:00
2.check the applicaiton traffic flowing through proper EAST /WEST IP servers (via splunk "server_host" element) | Hemanth/mani Divya/Nikhil | 2026-02-13 | 23:00
3.Check Activate lot status and last execution date in Espx table in DB (also check update_stock job weather it is in inprogress or completed) | Hemanth/mani Divya/Nikhil | 2026-02-13 | 23:00
4.Post Cron job start validate activateLot /updateLotShipmentDetails and application logs from splunk and elk | Hemanth/mani Divya/Nikhil | 2026-02-13 | 23:00
5.Validate NewRelic Logs | Hemanth/mani Divya/Nikhil | 2026-02-13 | 23:00
Post DR Drill
Sending status communication mail to Stakeholders | Gnanavel | 2026-02-13 | 23:00
Fusion Portal Update | Azeem | 2026-02-13 | 23:00
Closing of Change request and Ctasks | Azeem | 2026-02-13 | 23:00

## TaskPlan_DR_WEST
Pre-tasks |  | Date | EST Timing | IST Timing | Owner | Contact Details | Status
CDN Akamai west regeion should be configured | Ranil
Create a Change request for DR dryrun | Azeem Hirani
Run through the task list share it over an email | Gnanavel
Get the signoff for the plan | Nikhil
Send out an email to application team for the agreed dates for DR dry run | Gnanavel
End user communication or any other users to be informed | Nikhil
Check the App and Web Certificate Expiration | Venkata/Gnanavel
DR dryrun tasks
Wait for App team confirmation to check the current job is in completed state. | Hemanth/mani Divya/Nikhil
Bring down the services of West YZ webservers | Gnanavel/Nikhil
Disable the Cronjobs in both app & Webservers in Eastzone if anything required | Gnanavel
Switch over the Databse from West to East | Swarnavikram Mani/Madhusudhan
In Casino loadbalancer, disable West zone Servers pool application and internal | Gnanavel
Enable all required Cronjobs | Gnanavel
Request App team to perform app functionality validations | Gnanavel
Testing and Validation on West regeion
1.Validate Internal and External Application with Rep and test Customer login | Hemanth/mani Divya/Nikhil
2.check the applicaiton traffic flowing through proper East IP servers (via splunk "server_host" element) | Hemanth/mani Divya/Nikhil
3.Check Activate lot status and last execution date in Espx table in DB (also check update_stock job weather it is in inprogress or completed) | Hemanth/mani Divya/Nikhil
4.Post Cron job start validate activateLot /updateLotShipmentDetails and application logs from splunk and elk | Hemanth/mani Divya/Nikhil
5.Validate NewRelic Logs | Hemanth/mani Divya/Nikhil
DR dryrun success/failure | Hemanth/mani Divya/Nikhil
Rollback task
Disable all Cronjobs from west zone servers | Gnanavel
Start httpd services in west zone | Gnanavel/Nikhil
In Loadbalancer, enable west zone Servers pool in bot happlication and int | Gnanavel
Switch over the Databse from West to East | Swarnavikram Mani/Madhusudhan
Verify & Enable all required cronjobs in Eastzone | Gnanavel
Request application team to perform app functinality validations | Gnanavel
Testing and Validation post DR on east zone services
1.Validate Internal and External Application with Rep and test Customer login | Hemanth/mani Divya/Nikhil
2.check the applicaiton traffic flowing through proper EAST /WEST IP servers (via splunk "server_host" element) | Hemanth/mani Divya/Nikhil
3.Check Activate lot status and last execution date in Espx table in DB (also check update_stock job weather it is in inprogress or completed) | Hemanth/mani Divya/Nikhil
4.Post Cron job start validate activateLot /updateLotShipmentDetails and application logs from splunk and elk | Hemanth/mani Divya/Nikhil
5.Validate NewRelic Logs | Hemanth/mani Divya/Nikhil
Post DR Drill
Sending status communication mail to Stakeholders | Gnanavel
Fusion Portal Update | Azeem
Closing of Change request and Ctasks | Azeem

## Server Details
Non PROD
Non PROD | Dev1 | QA1 | Rev Dev | Rev QA | Dev2 (LT Env) | SIT 1 | SIT2 | AMI Details | PORT | Comments
APP Server | 10.119.98.170 | 10.119.99.100 | 10.119.99.238 | 10.119.98.126 | 10.119.97.27,10.119.101.197 | 10.119.99.34 | 10.119.98.111 | RHEL | 8085
UI Server | 10.119.98.242 | 10.119.98.255 | 10.119.97.37 | 10.119.97.36 | 10.119.97.14,10.119.100.250 | 10.119.98.255 | 10.119.98.44 | RHEL | 8900
YZ UI Server | 10.119.109.92 |  | - | - | - |  |  | RHEL | 8900
Slave Node | 10.119.100.109
PROD | PROD - EAST | PROD - EAST | PROD - WEST | PROD - WEST | AMI Details | PORT | Comments
APP Server | 144.70.96.18 | 144.70.102.37 | 144.70.115.97 | 144.70.118.96 | RHEL | 8085
UI Server | 144.70.103.43 | 144.70.99.51 | 144.70.113.121 | 144.70.117.125 | RHEL | 8900
YZ UI Server | 144.70.109.167 | 144.70.110.72 | 144.70.126.111 | 144.70.125.77 | RHEL | 8900
Slave Node
East | Ports
144.70.102.126 | 8085(Java), 2049(EFS Connection)
144.70.96.135 | 8085(Java), 2049(EFS Connection)
144.70.101.132 | 8443(Http)
144.70.99.201 | 8443(Http)
144.70.110.4 | 8443(Http)
144.70.109.42 | 8443(Http)
West | Ports
144.70.112.34 | 8085(Java), 2049(EFS Connection)
144.70.119.221 | 8085(Java), 2049(EFS Connection)
144.70.113.243 | 8443(Http)
144.70.118.186 | 8443(Http)
144.70.125.0 | 8443(Http)
144.70.127.161 | 8443(Http)