## TaskPlan_Bidsales_DR
Pre-tasks | Owner | Date | EST Timing | IST Timing | Contact Details | Status | Notes
Create a Change request for DR dryrun | Mahesh |  |  |  | 9497264759
Run through the task list share it over an email | Mahesh
Get the signoff for the plan | Sravani/Nikhil
Send out an email to application team for the agreed dates for DR dry run | Mahesh/Azeem
End user communication or any other users to be informed - App team, Business, PIPO team,SAP team | Sravani/Nikhil
Check the App and Web Certificate Expiration | Venkata/Gnanavel
Disable catchpoint alert during the activity | Sravani
DR dryrun tasks
Disable the Splunk /ELK Alert during the DR activity | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 | 9063726656/8489591980
Wait for App team confirmation to check the current job is in completed state. | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 | 9538811835/6268541826 | completed
Bring down the services of Eastzone App & webservers | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 |  | completed
Disable the Cronjobs in both app & Webservers in Eastzone | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 |  | completed
Stop the channels/feed from PIPO side- disable i700 feed | PIPO team/ Sampath Baddala | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 | 9901442645 | completed
Switch over the Databse from East to West | Rani/ Swarnavikram | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 | 9990639501/9052125556 | completed
TO check and confirm Reader and Writer instance in Postgre DB is same after switching DB | Rani/ Swarnavikram | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 |  | completed
Start the channels/feed from PIPO side-enable i700 feed | PIPO team/ Sampath Baddala | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 | 9901442645 | completed
In Casino loadbalancer, disable East zone Servers pool | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 |  | completed
In Casino LB Enable Westzone servers Pool | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 |  | completed
Start All services in WestZone (Both App & Web servers) | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 |  | completed
Enable all required Cronjobs | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30 |  | completed
Request App team to perform app functionality validations | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 21:00 | 2026-02-21 07:30
Testing and Validation on West region
1.Validate Internal and External Application with Rep and test Customer login | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 22:00
2.check the applicaiton traffic flowing through proper EAST /WEST IP servers (via splunk "server_host" element) | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 22:00
3.Check Activate lot status and last execution date in Espx table in DB (also check update_stock job weather it is in inprogress or completed) | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 22:00
4.Post Cron job start validate activateLot /updateLotShipmentDetails and application logs from splunk and elk | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 22:00
5.Validate NewRelic Logs | Sravani/Teja | 20/02/2026 | 2026-02-20 22:00
DR dryrun success/failure | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 22:00
Rollback task
Disable all Cronjobs from west zone servers | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 23:30
Stop All serives in Web & App servers from West Zone | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 23:30
In Loadbalancer, disable West zone Servers pool | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 23:30
In LB Enable East zone servers Pool | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 23:30
Stop the channels/feed from PIPO side-disable i700 feed | PIPO team/ Sampath Baddala | 20/02/2026 | 2026-02-20 23:30 |  | 9901442645
Switch over the Databse from West to East | Rani/ Swarnavikram | 20/02/2026 | 2026-02-20 23:30
Reader and Writer instance in Postgre DB is same after switching DB | Rani/ Swarnavikram
Start the channels/feed from PIPO side-enable i700 feed | PIPO team/ Sampath Baddala | 20/02/2026 | 2026-02-20 23:30 |  | 9901442645
start web & app servers in East zone | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 23:30
Verify & Enable all required cronjobs in Eastzone | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 23:30
Request application team to perform app functinality validations | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 23:30
Enable Health monitoring alert in Splunk | Venkata/Gnanavel | 20/02/2026 | 2026-02-20 23:30
Enable catchpoint Alert
Testing and Validation post DR on east zone services
1.Validate Internal and External Application with Rep and test Customer login | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 23:30
2.check the applicaiton traffic flowing through proper EAST /WEST IP servers (via splunk "server_host" element) | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 23:30
3.Check Activate lot status and last execution date in Espx table in DB (also check update_stock job weather it is in inprogress or completed) | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 23:30
4.Post Cron job start validate activateLot /updateLotShipmentDetails and application logs from splunk and elk | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 23:30
5.Validate NewRelic Logs | Sravani/Teja | 20/02/2026 | 2026-02-20 23:30
Application team needs to validate if any duplicate records getting created | Mani Divya & Preetam | 20/02/2026 | 2026-02-20 23:30
Post DR Drill tasks
Sending status communication mail to Stakeholders | Venkata/Gnanavel | 2026-02-21 | 2026-02-21 02:00
Fusion Portal Update (Only During Main DR activity) | Azeem | 2026-02-21 | 2026-02-21 02:00
Closing of Change request and Ctasks | Venkata/Gnanavel | 2026-02-21 | 2026-02-21 02:00

## Server Details
East Zone Server List |  | Current services status (Before DR) | Service status during DR | Server status Post DR
GTS-D31V-BIDSALES-PROD-12DEC25-GZ-App-ASG | 144.70.96.148 | Up | Down | Up
GTS-D31V-BIDSALES-PROD-12DEC25-GZ-App-ASG | 144.70.99.126 | Up | Down | Up
GTS-D31V-BIDSALES-PROD-12DEC25-GZ-Web-ASG | 144.70.98.238 | Up | Down | Up
GTS-D31V-BIDSALES-PROD-12DEC25-GZ-Web-ASG | 144.70.97.109 | Up | Down | Up
GTS-D31V-BIDSALES-PROD-12DEC25-YZ-Web-ASG | 144.70.108.249 | Up | Down | Up
GTS-D31V-BIDSALES-PROD-12DEC25-YZ-Web-ASG | 144.70.108.153 | Up | Down | Up
West Zone Server List
GTS-D31V-BIDSALES-WEST2-DR-PROD-12DEC25-YZ-Web-ASG | 144.70.124.148 | Up | Up | Down
GTS-D31V-BIDSALES-WEST2-DR-PROD-12DEC25-YZ-Web-ASG | 144.70.124.184 | Up | Up | Down
GTS-D31V-BIDSALES-WEST2-DR-PROD-12DEC25-GZ-Web-ASG | 144.70.114.201 | Down | Up | Down
GTS-D31V-BIDSALES-WEST2-DR-PROD-12DEC25-GZ-Web-ASG | 144.70.115.68 | Down | Up | Down
GTS-D31V-BIDSALES-WEST2-DR-PROD-12DEC25-GZ-App-ASG | 144.70.115.180 | Down | Up | Down
GTS-D31V-BIDSALES-WEST2-DR-PROD-12DEC25-GZ-App-ASG | 144.70.115.92 | Down | Up | Down